# Proposal: Proton Integration with Playwright Framework

Prepared by: Altimetrik

Date: June 11, 2026

Version: 1.0

## Table of Contents

1. [Framework Background](#1-framework-background)

2. [Project Scope](#2-project-scope)

3. [Architecture](#3-architecture)

4. [Effort Estimate](#4-effort-estimate)

5. [Project Timeline](#5-project-timeline)

6. [Team Structure](#6-team-structure)

7. [Commercials](#7-commercials)

8. [Assumptions and Dependencies](#8-assumptions-and-dependencies)

## 1. Framework Background

### Playwright Test Automation Framework

Playwright is a modern, open-source end-to-end test automation framework developed by Microsoft. It supports multiple browsers (Chromium, Firefox, WebKit) and provides robust tooling for UI and API testing. The existing framework has been designed and implemented to support automated regression and functional testing with the following characteristics:

Test Execution: Automated test suites executed via CI/CD pipelines

Reporting: JSON-based results (results.json) and PDF report generation

Test Management Integration: Currently integrated with Xray (Jira-native test management), including pre-execution approval checks via API

Result Submission: Automated test result upload to the test management platform post-execution

### Proton Test Management Platform

Proton is the target test management platform to which the Playwright framework will be integrated. The integration will mirror the existing Xray integration pattern, leveraging Proton's REST API to:

Create and manage test runs

Submit test execution results

Upload file attachments (PDF reports)

Validate test case approval status prior to execution

This integration enables seamless traceability between automated test execution and Proton's test management workflows, replacing or supplementing the current Xray integration.

## 2. Project Scope

### In Scope

The following activities are included in this engagement:

| # | Activity | Description |
| --- | --- | --- |
| 1 | API Discovery & Analysis | Analyse Proton's REST API documentation, endpoints, authentication mechanism, and data models relevant to test run creation, result submission, and attachment upload |
| 2 | Framework Design | Design the integration layer within the existing Playwright framework to support Proton as a test management target |
| 3 | Development | Implement the Proton integration module, including: test run creation, result mapping (Jira/Proton IDs), approval status validation, result submission, and PDF attachment upload |
| 4 | CI/CD Pipeline Update | Update existing pipeline configuration to support the Proton integration flow (approval check → execution → result upload) |
| 5 | Testing & Validation | End-to-end validation of the integration against a Proton sandbox environment, covering positive, negative, and edge-case scenarios |
| 6 | UAT Support & Rework | Support Proton stakeholders during UAT, address feedback, and deliver a final production-ready integration |

### Out of Scope

Modifications to Proton platform itself

Creation or management of Proton test cases

Changes to existing Playwright test scripts beyond integration wiring

Infrastructure provisioning for CI/CD pipelines

Migration of historical test results into Proton

## 3. Architecture

### High-Level Integration Architecture

┌─────────────────────────────────────────────────────────────┐
│                        CI/CD Pipeline                        │
│                                                             │
│  ┌──────────────┐    ┌─────────────────┐    ┌───────────┐  │
│  │  Trigger /   │───▶│  Approval Check │───▶│  Execute  │  │
│  │  Schedule    │    │  (Proton API)   │    │  Tests    │  │
│  └──────────────┘    └─────────────────┘    └─────┬─────┘  │
│                                                   │         │
│                                         ┌─────────▼──────┐  │
│                                         │  Generate       │  │
│                                         │  results.json  │  │
│                                         │  + PDF Report  │  │
│                                         └─────────┬──────┘  │
│                                                   │         │
│                                         ┌─────────▼──────┐  │
│                                         │  Proton         │  │
│                                         │  Integration    │  │
│                                         │  Module         │  │
│                                         └─────────┬──────┘  │
└───────────────────────────────────────────────────┼─────────┘
                                                    │
                              ┌─────────────────────▼──────────────┐
                              │         Proton REST API             │
                              │  ┌──────────────────────────────┐  │
                              │  │ POST /test-runs               │  │
                              │  │ POST /test-runs/{id}/results  │  │
                              │  │ POST /test-runs/{id}/attach   │  │
                              │  │ GET  /test-cases/{id}/status  │  │
                              │  └──────────────────────────────┘  │
                              └────────────────────────────────────┘

### Integration Module Components

| Component / File | Responsibility |
| --- | --- |
| protonIntegration.groovy | Core integration script — handles HTTP communication with Proton REST API, test run creation, result submission, PDF attachment upload, and error handling for both Standalone and Regression execution modes |
| validateProtonTestCase.groovy | Pre-execution approval validation — queries Proton API for test case approval status and gates pipeline execution (mirrors existing Xray approval check pattern) |
| Jenkinsfile (updated) | Pipeline definition updated to wire all three language runners (TypeScript, JavaScript, Python) through the Proton integration and approval validation steps |

### Technology Stack

| Layer | Technology |
| --- | --- |
| Test Framework | Playwright (TypeScript / JavaScript / Python) |
| Integration Scripts | Groovy (protonIntegration.groovy, validateProtonTestCase.groovy) |
| CI/CD | Jenkins (Jenkinsfile — all three language runners updated) |
| Test Management | Proton (via REST API, JSON/HTTPS) |
| Reporting | results.json + PDF (existing format, reused as-is) |
| ID Mapping | Jira IDs (e.g., DNIGMP-188) mapped to Proton test case IDs |

### Code Reuse

Approximately 80% of the existing Xray integration code will be reused, with the Proton integration module replacing only the API client and endpoint-specific logic.

## 4. Effort Estimate

### Activity Breakdown

| Activity | Effort (Person Days) | Notes |
| --- | --- | --- |
| Discovery, Design & Development | 40 | API analysis, integration design, implementation, pipeline updates |
| Testing and Validation | 20 | Sandbox testing, regression, edge cases, CI/CD validation |
| Rework as per UAT Feedback | 10 | Incorporating stakeholder feedback post-UAT |
| Total Person Days | 70 |  |
| Total Person Months | 3 | Based on 21 working days/month |

### Key Metrics

| Parameter | Value |
| --- | --- |
| FTE Required | 1 |
| Working Days per Month | 21 |
| Project Duration | 3 Months |

## 5. Project Timeline

### 13-Week Delivery Plan

| Weeks | Phase | Key Deliverables |
| --- | --- | --- |
| 1–3 | Discovery | Proton API documentation reviewed, connectivity confirmed, concept map produced, design document signed off by stakeholders |
| 4–7 | Core Integration | protonIntegration.groovy — full implementation covering Standalone execution, Regression execution, and error handling |
| 8–9 | Approval Validation | validateProtonTestCase.groovy — approval status check wired into pipeline pre-execution checks (mirrors existing Xray pattern) |
| 9 | Pipeline Wiring | All three language runners (TypeScript / JavaScript / Python) and Jenkinsfile updated to route through Proton integration |
| 10–12 | Testing & Validation | End-to-end tests across all language runners, failure scenario coverage, sandbox regression runs |
| 12–13 | UAT & Rework | UAT execution with Proton stakeholders, rework based on feedback, production deployment, knowledge transfer |

### Milestone Summary

| Milestone | Target Week |
| --- | --- |
| Design Document Signed Off | Week 3 |
| protonIntegration.groovy Complete | Week 7 |
| validateProtonTestCase.groovy & Pipeline Wiring Complete | Week 9 |
| End-to-End Testing Complete (all runners) | Week 12 |
| UAT Sign-Off & Production Go-Live | Week 13 |

## 6. Team Structure

### Proposed Team

| Role | Headcount | Responsibilities |
| --- | --- | --- |
| Senior Test Automation Engineer | 1 (FTE) | End-to-end delivery: API analysis, design, development, testing, UAT support, documentation |

### Collaboration Requirements (Proton Team)

The Proton team is requested to provide approximately 3 days of collaboration spread across the 12-week engagement, covering:

API onboarding and credential/access provisioning

Clarification of test case ID mapping and data model queries

UAT participation and sign-off

## 7. Commercials

### Pricing Summary

| Parameter | Value |
| --- | --- |
| Engagement Model | Fixed Price |
| Average Day Rate (ADR) | CHF 181 |
| Working Days per Month | 21 |
| Monthly Cost | CHF 3,801 |
| Project Duration | 3 Months |
| Total Project Cost | CHF 11,403 |

### Cost Breakdown by Phase

| Phase | Person Days | Cost (CHF) |
| --- | --- | --- |
| Discovery, Design & Development | 40 | 7,240 |
| Testing and Validation | 20 | 3,620 |
| Rework as per UAT Feedback | 10 | 1,810 |
| Total | 70 | 12,670 |

Note: The fixed project cost is CHF 11,403 based on the agreed monthly rate. Any scope changes beyond what is defined in Section 2 will be subject to a formal change request and revised pricing.

### Payment Terms

| Milestone | Payment (%) | Amount (CHF) |
| --- | --- | --- |
| Project Kickoff | 30% | 3,421 |
| Development Complete (Week 9) | 40% | 4,561 |
| UAT Sign-Off & Go-Live (Week 12) | 30% | 3,421 |
| Total | 100% | 11,403 |

## 8. Assumptions and Dependencies

### Assumptions

| # | Assumption |
| --- | --- |
| A1 | Proton exposes a REST API (JSON/HTTPS) that supports creating test runs, submitting results, and uploading file attachments programmatically. Without this, integration is not feasible. |
| A2 | Proton test cases use the same IDs as Jira (e.g., DNIGMP-188) or a clear, queryable mapping exists between the two systems. |
| A3 | Proton exposes a test case approval status via API so the pipeline can validate approval before execution — same pattern as the current Xray check. |
| A4 | A Proton sandbox/test project is available for development and testing (Weeks 4–12) to avoid polluting live data. |
| A5 | The existing PDF report format and results.json structure are accepted by Proton stakeholders without modification (~80% of existing code is reused as-is). |
| A6 | The Proton team is available for approximately 3 days of collaboration (API questions, test data, UAT sign-off) spread across the 12 weeks. |
| A7 | Existing CI/CD pipeline infrastructure is in place and accessible; no new infrastructure provisioning is required as part of this engagement. |
| A8 | All required API credentials, access tokens, and sandbox environment details will be provided to the Altimetrik team by the end of Week 1. |

### Dependencies

| # | Dependency | Owner | Required By |
| --- | --- | --- | --- |
| D1 | Proton REST API documentation and access credentials | Proton Team | Week 1 |
| D2 | Proton sandbox environment provisioned and accessible | Proton Team | Week 4 |
| D3 | Confirmation of Jira-to-Proton ID mapping approach | Proton Team | Week 3 |
| D4 | Approval status API endpoint confirmed and documented | Proton Team | Week 3 |
| D5 | UAT participants identified and availability confirmed | Customer | Week 10 |
| D6 | Access to existing Playwright framework codebase and CI/CD pipeline | Customer / Altimetrik | Week 1 |

### Risks

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Proton API does not support required operations (test run creation, attachment upload) | Low | High | Early API discovery in Week 1–2; escalate immediately if gaps identified |
| R2 | Jira-to-Proton ID mapping is complex or requires custom logic | Medium | Medium | Allocate buffer in design phase; clarify mapping by Week 3 |
| R3 | Proton sandbox unavailable during development | Low | High | Confirm sandbox access before Week 4; raise as blocker if delayed |
| R4 | UAT feedback requires significant rework beyond 10 days | Low | Medium | Early stakeholder alignment on acceptance criteria before UAT begins |

## Acceptance

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by (Altimetrik) |  |  |  |
| Approved by (Customer) |  |  |  |

*This proposal is valid for 30 days from the date of issue.*

*All costs are in CHF and exclusive of applicable taxes unless otherwise stated.*